## Sheet1
ProjectID | ProjectName | Location | StartDate | EndDate | PlannedCost | ActualCost | PlannedProgress% | ActualProgress% | ProjectManager | Contractor | Status | DelayDays | LaborCount | Remarks
P001 | Maintenance | Al Ain | 2025-03-07 | 2025-07-04 | 881859 | 890689 | 60 | 63 | Eng. Franco | Bright Deal | Ongoing | 15 | 15 | Material delay
P002 | Maintenance | Al Dhafra | 2025-03-09 | 2025-06-09 | 575420 | 636931 | 80 | 72 | Eng. Antonio | Mountain View | Delayed | 0 | 23 | Closed
P003 | Mosque | Al Dhafra | 2025-04-17 | 2025-10-12 | 857949 | 991633 | 100 | 81 | Eng. Franco | Bright Deal | Ongoing | 15 | 14 | Closed
P004 | Slaughterhouse | Al Dhafra | 2025-05-09 | 2025-07-31 | 855924 | 951927 | 80 | 72 | Eng. Osama | Silver Line | Completed | 0 | 16 | Under approval
P005 | Maintenance | Abu Dhabi | 2025-02-06 | 2025-07-09 | 806254 | 930500 | 90 | 96 | Eng. Antonio | Imdaad | Completed | 5 | 30 | Under approval
P006 | Wall | Abu Dhabi | 2025-01-01 | 2025-04-22 | 699390 | 701478 | 50 | 47 | Eng. Nasser | Al Falah | Delayed | 15 | 28 | Handover done
P007 | Maintenance | Bani Yas | 2025-05-20 | 2025-09-20 | 442413 | 462594 | 50 | 44 | Eng. Aisha | Basco | Ongoing | 10 | 14 | Closed
P008 | Wall | Bani Yas | 2025-05-01 | 2025-09-05 | 713919 | 719323 | 60 | 60 | Eng. Nasser | Basco | Completed | 0 | 10 | Pending inspection
P009 | School | Al Dhafra | 2025-04-16 | 2025-06-18 | 695052 | 720775 | 100 | 100 | Eng. Nasser | Basco | Completed | 10 | 27 | Material delay
P010 | Slaughterhouse | Abu Dhabi | 2025-05-08 | 2025-09-10 | 788451 | 924246 | 60 | 48 | Eng. Antonio | Bright Deal | Completed | 5 | 26 | Handover done
P011 | Wall | Al Ain | 2025-06-02 | 2025-10-18 | 706899 | 707351 | 50 | 50 | Eng. Asim | Bright Deal | Completed | 15 | 12 | Closed
P012 | Slaughterhouse | Al Dhafra | 2025-04-02 | 2025-08-21 | 503209 | 593279 | 100 | 86 | Eng. Rami | Bright Deal | Completed | 5 | 18 | Handover done
P013 | Slaughterhouse | Bani Yas | 2025-06-04 | 2025-08-08 | 833501 | 912261 | 50 | 52 | Eng. Asim | Silver Line | Delayed | 0 | 19 | Material delay
P014 | School | Abu Dhabi | 2025-01-06 | 2025-05-01 | 641712 | 622200 | 100 | 95 | Eng. Asim | Golden Tech | Ongoing | 5 | 18 | Under approval
P015 | Wall | Al Ain | 2025-01-14 | 2025-05-13 | 796047 | 757646 | 100 | 100 | Eng. Franco | Imdaad | Completed | 10 | 27 | Pending inspection
P016 | Maintenance | Bani Yas | 2025-01-04 | 2025-04-26 | 811851 | 733872 | 90 | 76 | Eng. Franco | Mountain View | Completed | 10 | 27 | Material delay
P017 | Slaughterhouse | Abu Dhabi | 2025-06-08 | 2025-12-05 | 773801 | 863200 | 100 | 81 | Eng. Nasser | Silver Line | Ongoing | 15 | 18 | Closed
P018 | Wall | Abu Dhabi | 2025-04-16 | 2025-09-28 | 721786 | 690622 | 100 | 100 | Eng. Antonio | Imdaad | Delayed | 15 | 12 | Closed
P019 | Mosque | Abu Dhabi | 2025-04-06 | 2025-06-26 | 823593 | 894288 | 50 | 51 | Eng. Nasser | Golden Tech | Completed | 0 | 10 | Material delay
P020 | Maintenance | Al Ain | 2025-05-08 | 2025-08-17 | 670346 | 799989 | 80 | 84 | Eng. Franco | Silver Line | Ongoing | 0 | 16 | Pending inspection